واٹس ایپ آٹومیشن SaaS

Official WhatsApp Business API + Chatbot + Inbox + CRM + Campaigns

Project Handout — From Zero to Launch Plan

یہ handout project folder میں رکھنے کے لیے بنایا گیا ہے۔ اس میں business direction، phases، architecture، database، security، deployment، beta launch اور proof checklist شامل ہے۔

Important Decision: API key seller نہیں بننا؛ official WhatsApp automation SaaS provider بننا ہے۔

Prepared Date: 9 June 2026

# 1. Executive Summary

اس project کا مقصد ایک professional SaaS platform بنانا ہے جہاں businesses اپنا official WhatsApp Business account/number connect کر کے customer support، chatbot automation، CRM، templates اور campaigns manage کر سکیں۔

• Product کو raw API key selling کے طور پر launch نہیں کرنا۔

• ہر client کا اپنا Meta Business / WABA / WhatsApp number ہونا چاہیے۔

• آپ dashboard، automation، inbox، integrations، reporting اور support sell کریں گے۔

• Compliance، opt-in، security، encrypted tokens اور tenant isolation لازمی ہوں گے۔

# 2. Correct Business Positioning

| غلط طریقہ | صحیح طریقہ |
| --- | --- |
| Raw API key یا shared token بیچنا | Official WhatsApp Automation SaaS sell کرنا |
| ایک number/token کو multiple clients کو دینا | ہر client کا اپنا WABA/phone number connect کروانا |
| Spam sender یا bulk blast tool بنانا | Opt-in based campaign + CRM + support tool بنانا |
| Unofficial QR/WhatsApp Web automation | Official Meta WhatsApp Business Platform use کرنا |

Professional market wording:

• Official WhatsApp Business API Setup + Automation Dashboard

• WhatsApp Chatbot, CRM Inbox & Business Automation SaaS

• Connect your official WhatsApp Cloud API and automate support, leads, orders, and campaigns.

# 3. Phase-wise Roadmap

| Phase | Focus | Main Output |
| --- | --- | --- |
| Phase 0 | Business direction lock | API key seller نہیں، SaaS provider model |
| Phase 1 | Market validation | Target customers, pricing, beta clients |
| Phase 2 | Official Meta setup | Developer app, test number, webhook test |
| Phase 3 | Tech stack | Next.js, PostgreSQL, Prisma, Auth, hosting plan |
| Phase 4 | Database design | Multi-tenant schema + secure token storage |
| Phase 5 | MVP screens | Landing, dashboard, inbox, settings, admin |
| Phase 6 | Manual WhatsApp connection | WABA ID, phone ID, token, test send |
| Phase 7 | Webhook system | Incoming messages saved and shown |
| Phase 8 | Send message system | Dashboard سے WhatsApp reply |
| Phase 9 | Inbox MVP | Live chat inbox |
| Phase 10 | Basic chatbot | Keyword/reply automation |
| Phase 11 | Templates | Approved template management |
| Phase 12 | Contacts + campaigns | Opt-in based campaigns |
| Phase 13 | Billing + usage | Plans, limits, usage logs |
| Phase 14 | Security hardening | Encryption, isolation, rate limits |
| Phase 15 | Deployment | Live production setup |
| Phase 16 | Beta launch | 3–5 real clients |
| Phase 17 | Embedded Signup | Automated onboarding |
| Phase 18 | Agency white-label | Reseller/agency model |

# 4. Phase 0 — Business Direction Lock

Goal: project کی official اور safe direction lock کرنا۔

• Offer: Official WhatsApp API setup + Chatbot + Inbox + CRM + Campaigns.

• Avoid: raw API keys، rented numbers، shared tokens، unofficial WhatsApp Web automation.

• Target customers: ecommerce stores، clinics/salons، real estate، service businesses، agencies.

• Primary revenue: setup fee + monthly SaaS subscription + add-ons.

# 5. Phase 1 — Market Validation

Goal: coding سے پہلے demand verify کرنا۔

1. 20 potential clients سے بات کریں۔

2. ہر client سے پوچھیں کہ روز WhatsApp پر کتنے messages آتے ہیں۔

3. Auto reply، team inbox، campaign، order notification اور CRM needs note کریں۔

4. 3 beta clients identify کریں جو real testing کر سکیں۔

5. Starter، Growth، Agency pricing estimate بنائیں۔

Output: target customer، beta clients، pricing، must-have features۔

# 6. Phase 2 — Official Meta Setup

Goal: Meta Developer app اور WhatsApp test environment ready کرنا۔

• Meta Business Portfolio

• Meta Developer App

• WhatsApp product

• Test WABA and test phone number

• Webhook verify endpoint

• Send/receive test message

SMS verification issue handling:

• Fresh business number use کریں۔

• SMS اور voice call دونوں receive ہونے چاہئیں۔

• Number پہلے WhatsApp/Cloud API میں conflict نہ کر رہا ہو۔

• SMS fail ہو تو voice call verification try کریں۔

• Client کو checklist دیں: SIM active، SMS blocking off، call forwarding off، number accessible۔

# 7. Phase 3 — Recommended Tech Stack

| Area | Recommended Option |
| --- | --- |
| Frontend | Next.js + Tailwind CSS |
| Backend | Next.js API Routes یا Node.js/NestJS |
| Database | PostgreSQL |
| ORM | Prisma |
| Auth | NextAuth/Auth.js, Clerk, یا Supabase Auth |
| Payments | Stripe/Paddle یا local manual invoice initially |
| Hosting | Vercel + Railway/Render/Supabase |
| Queue later | BullMQ + Redis / Upstash |
| Logs later | Sentry / Logtail |

MVP میں simple monorepo رکھیں۔ پہلے complexity کم رکھیں، پھر scale کریں۔

# 8. Phase 4 — Database Design

Goal: multi-client SaaS structure بنانا جہاں ہر client کا data isolated ہو۔

• users

• tenants

• team_members

• whatsapp_accounts

• phone_numbers

• access_tokens

• contacts

• conversations

• messages

• message_templates

• automations

• campaigns

• webhook_events

• usage_logs

• invoices

• audit_logs

Critical rule: ہر business record میں tenantId لازمی ہو۔ ایک client کا data دوسرے client کو کبھی نظر نہیں آنا چاہیے۔

# 9. Phase 5 — MVP Screens

| Public Website | Client Dashboard | Admin Dashboard |
| --- | --- | --- |
| Home page | Dashboard overview | All clients |
| Pricing page | Connect WhatsApp | Connected numbers |
| Features page | Inbox | Message usage |
| Contact page | Contacts | Failed webhooks |
| Login/signup | Templates | Subscription status |
| Privacy + Terms | Settings + Billing | Abuse/spam monitoring |

# 10. Phase 6 — Manual WhatsApp Connection MVP

شروع میں Embedded Signup کے بجائے manual setup رکھیں تاکہ API flow مکمل سمجھ آ جائے۔

• Client Business Name

• WABA ID

• Phone Number ID

• Access Token — encrypted storage only

• Webhook Verify Token

• Connection Status

• Send Test Message button

• Incoming Webhook Test

Important: token کبھی frontend میں show نہ ہو۔ صرف connection status دکھائیں۔

# 11. Core Product Build — Webhook, Messages, Inbox, Bot, Templates, Campaigns

## 11.1 Webhook System

• /api/webhooks/whatsapp endpoint

• GET request سے webhook verification

• POST payload کو webhook_events میں save کرنا

• Incoming message extract کر کے contact/conversation/message save کرنا

• Processing status اور error logs save کرنا

## 11.2 Send Message System

• Backend tenant ownership verify کرے

• WhatsApp API call backend سے ہو

• Message status save ہو: sent, delivered, read, failed

• Error user-friendly انداز میں dashboard پر show ہو

## 11.3 Inbox MVP

• Conversation list

• Customer profile

• Message thread

• Reply box

• Unread count

• Agent assignment later

## 11.4 Basic Chatbot Builder

• Keyword trigger

• Welcome message

• Fallback message

• Office-hours reply

• Human handoff

## 11.5 Templates + Campaigns

• Approved template list

• Variables preview

• Contacts import

• Opt-in status required

• Unsubscribe/STOP handling

• Campaign failure report

# 12. Phase 13 — Billing + Usage

| Plan | Best For | Included |
| --- | --- | --- |
| Starter | Small shops | 1 number, basic inbox, basic bot, limited contacts |
| Growth | Growing businesses | Team inbox, automations, templates, campaigns |
| Agency | Marketing agencies | Multiple clients, white-label, reports |

• Usage logs: messages sent, delivered, failed, category, tenantId, billing period.

• Setup fee ضرور رکھیں کیونکہ onboarding اور verification میں time لگتا ہے۔

# 13. Phase 14 — Security Hardening

• Access tokens encrypted storage

• Tokens frontend میں کبھی نہ جائیں

• Tenant-based data isolation

• Auth-protected dashboard

• Backend-level admin route protection

• Webhook verification

• Rate limiting

• Audit logs

• CORS production domains only

• Secrets logs/error messages میں نہ آئیں

• .env کبھی GitHub پر upload نہ ہو

• Database backup plan

# 14. Phase 15 — Deployment Plan

Recommended deployment:

• Frontend: Vercel

• Backend/API: Vercel functions, Railway, یا Render

• Database: Supabase/Railway PostgreSQL

• Domain + SSL: Cloudflare/Vercel

• Logs: Sentry

• Email: Resend/SendGrid

Deployment checklist:

• Production .env set

• Database migrations applied

• Webhook URL live domain پر set

• HTTPS working

• CORS production domain allowed

• Build pass

• Login working

• Dashboard working

• Send/receive message working

• Logs visible

# 15. Phase 16 — Beta Launch

• صرف 3–5 clients onboard کریں۔

• ہر client کا اپنا WhatsApp number ہو۔

• Contacts کے opt-in کی written confirmation لیں۔

• Daily logs check کریں۔

• Failed messages investigate کریں۔

• Client feedback collect کریں۔

• Bugs fix کریں۔

• Pricing validate کریں۔

Beta success criteria: 7 دن webhook stable رہے، messages send/receive ہوں، tenant data leak نہ ہو، اور کم از کم 1 client paid plan پر آئے۔

# 16. Phase 17–18 — Embedded Signup + Agency White-label

MVP stable ہونے کے بعد manual connection کو Embedded Signup میں upgrade کریں۔ پھر agency/white-label model add کریں۔

• Connect WhatsApp button

• Meta login flow

• Business/WABA/phone assets capture

• Token exchange

• Auto database setup

• Custom agency logo/domain

• Agency clients, limits, billing, reports

# 17. 90-Day Execution Timeline

| Time | Main Focus | Expected Result |
| --- | --- | --- |
| Days 1–15 | Market validation + Meta test setup | Beta clients + send/receive test |
| Days 16–30 | Auth, database, dashboard, manual connect | MVP foundation |
| Days 31–45 | Webhook, send message, inbox | Live chat usable |
| Days 46–60 | Bot, templates, contacts | Automation layer |
| Days 61–75 | Campaigns, billing, admin | Paid SaaS structure |
| Days 76–90 | Deployment, security, beta launch | Production beta |

# 18. Proof Gate — ہر Phase قبول کرنے سے پہلے

کسی phase کو complete/done/ready تب تک قبول نہ کریں جب تک evidence نہ ملے۔

• Files changed

• Commands run

• Pass/fail output

• Build/lint/type-check/test result

• API endpoint proof if backend involved

• Browser page proof if frontend involved

• Console error check

• Screenshot proof for UI

• Database/migration proof if DB involved

• Remaining issues, risks, next recommended step

# 19. Main Risks and Controls

| Risk | Control |
| --- | --- |
| SMS verification fail | Fresh number, SMS/call readiness checklist, voice call option |
| Meta account ban | Official API, opt-in, no spam, compliance logs |
| Token leak | Encryption, no frontend exposure, restricted admin access |
| Tenant data leakage | tenantId everywhere, backend authorization checks |
| High message cost | Usage logs, limits, billing alerts |
| Webhook instability | Raw event logs, retry status, monitoring |
| Client misuse | Campaign limits, abuse detection, opt-out enforcement |

# 20. Final Project Manager Decision

Approved direction: Official WhatsApp Automation SaaS Provider.

Rejected direction: Raw API key seller, shared token seller, unofficial QR automation, or spam sender.

Next practical step: Phase 1 market validation اور Phase 2 Meta test setup complete کریں۔ Coding تب شروع کریں جب official test API سے send/receive message successfully ہو جائے۔

# 21. Official References

• WhatsApp Business Platform: https://whatsappbusiness.com/products/business-platform/

• WhatsApp Business Messaging Policy: https://business.whatsapp.com/policy/

• Meta WhatsApp Cloud API Docs: https://developers.facebook.com/docs/whatsapp/

• WhatsApp Webhooks: https://developers.facebook.com/docs/whatsapp/cloud-api/webhooks/

• Embedded Signup: https://developers.facebook.com/docs/whatsapp/embedded-signup/

• WhatsApp Platform Pricing: https://whatsappbusiness.com/products/platform-pricing/